## TESTCASES
Project Name | Revenue Collection System | Developer Name |  | JAMES MUNIU | Pre-requisite | Total Test Cases | 51
Product Name | Revenue Collection System | Developer Test Evidence |  | YES | System hosted and running | Test cases tested | 51
Version | 1.0.0.100420251315 | Test Designed by |  | MERCELYN KADIMA | Running scripts | To be Tested | 0
Release Number | 1 | QA Engineer Name |  | MERCELYN KADIMA |  | Blocked | 0
Target Client | NCBA | QA Report date |  | 2025-07-02 |  | Passed | 48
Applicable Branch | NAIROBI | Environment |  | Test Server |  | Failed
Country | KENYA
S.NO | REQUIREMENT ID | TEST CASE ID | MODULE | SCENARIO DESCRIPTION | TEST CASE DESCRIPTION | PRECONDITION | TEST DATA | EXPECTED RESULT | POSTCONDITION | ACTUAL DATA | STATUS | DEFECT ID | COMMENTS
|  | RCS001 | CUSTOMER PORTAL | Customer registration via self-service portal. | 1. Navigate to self-service portal. 2. Click “Register.” 3. Enter Name, email, Phone, Password. 4. Submit the registration form. | System running; Registration page accessible. | Name: Phone: email Password | Account is created successfully. Success message displayed. SMS confirmation sent to registered phone number. | New account stored in database. | UNSUCCESSFUL | FAILED
|  | RCS002 | CUSTOMER PORTAL | Customer registration via self-service portal. | 1. Navigate to self-service portal. 2. Click “Register.” 3. Enter Name, email, Phone, Password. 4. Submit the registration form. | System running; Registration page accessible. | Name: Phone: email Password | Account is created successfully. Success email displayed. email confirmation sent to registered email address. | New account stored in database. | SUCCESSFUL | PASSED
|  | RCS003 | CUSTOMER PORTAL | Registration fails with missing mandatory fields. | 1. Navigate to self-service portal. 2. Click “Register.” 3. Leave Phone Number blank. 4. Submit form. | System running. | Name, Email, Phone: (blank), Password | Error message “Phone number is required.” No account created. | No database record created. | SUCCESSFUL | PASSED
|  | RCS004 | CUSTOMER PORTAL | login with valid credentials. | 1. Navigate to Login page. 2. Enter valid email and password. 3. Click “Login.” | Valid account exists. | Email Password | Redirected to dashboard. Login recorded in audit log. | Active user session. | SUCCESSFUL | PASSED
|  | RCS005 | CUSTOMER PORTAL | login fails with invalid password. | 1. Navigate to Login page. 2. Enter valid email and wrong password. 3. Click “Login.” | Valid account exists. | Email Password | Error message “Invalid credentials.” No session created. | No changes in user session data. | SUCCESSFUL | PASSED
|  | RCS006 | CUSTOMER PORTAL | Password reset via “Forgot Password” link. | 1. Click “Forgot Password.” 2. Enter registered phone number. 3. Receive OTP via SMS. 4. Enter OTP and new password. | Account exists with registered email address. | New Password | Confirmation message displayed. | New password stored in system. | SUCCESSFUL | PASSED
|  | RCS007 | CUSTOMER PORTAL | account details update is successful. | 1. Login to portal. 2. Go to “Account Settings.” 3. Change phone number. 4. Save changes. | Customer logged in. | New Phone | Account details updated successfully. Confirmation message displayed. | Updated data stored in database. | SUCCESSFUL | PASSED
|  | RCS008 | CUSTOMER PORTAL | invalid phone number format is rejected during update. | 1. Login to portal. 2. Go to “Account Settings.” 3. Enter invalid phone format (e.g., 1234). 4. Save changes. | Customer logged in. | Phone | Error message “Invalid phone number format.” No changes saved. | Original phone remains in system. | SUCCESSFUL | PASSED
|  | RCS009 | CUSTOMER PORTAL | customer can view payment history. | 1, Login as customer. 2. Navigate to “Payment History.” | Customer has at least one completed payment. | N/A | List of payments displayed with Date, Amount, Vehicle Reg. Option to view individual receipts. | No changes to database. | SUCCESSFUL | PASSED
|  | RCS010 | CUSTOMER PORTAL | empty payment history is handled gracefully. | Login as customer with no past transactions. Go to “Payment History.” | New account, no transactions recorded. | N/A | Message “No payment history found.” | No changes to database. | SUCCESFUL | PASSED
|  | RCS011 | CUSTOMER PORTAL | customer can download payment receipt from history. | 1. Login as customer. 2. Open “Payment History.” 3. Select a payment. 4. Click “Download Receipt.” | Payment record exists. | Payment | Receipt downloaded in PDF format. Details match stored transaction data. | No database changes. | SUCCESSFUL | PASSED
|  | RCS012 | CUSTOMER PORTAL | customer is logged out after session timeout. | 1. Login to portal. 2. Stay idle for timeout duration. 3. Attempt to navigate to another page. | Session timeout | N/A | Redirected to login page. Message: “Session expired.” | Session terminated. | UNSUCCESFUL | FAILED
|  | RCS013 | CUSTOMER PORTAL | customer can upload a profile picture during registration. | Navigate to self-service portal → Register. Fill in all required fields. Click “Upload Profile Picture” and select a valid image file. Submit form. | Supported image formats: JPG, PNG; Max size 2MB. | Profile Pic | Account created with profile picture linked to profile. | Profile picture stored in system and visible in dashboard. | SUCCESSFUL | PASSED
|  | RCS014 | CUSTOMER PORTAL | customer can update profile picture from account settings. | 1. Login to customer portal. 2. Navigate to “Account Settings.” 3. Click “Change Profile Picture.” 4. Select a new valid image file. 5. Save changes. | Customer account exists with an existing profile picture. | new profile picture | Profile picture updated successfully. New image displayed immediately on dashboard. | Old profile picture replaced in storage. | SUCCESSFUL | PASSED
|  | RCS015 | CUSTOMER PORTAL | Initiate Payment button functionality | 1. Navigate to Payment section. 2. Click Initiate Payment button. | Customer is logged into the portal. There is an outstanding balance. | Customer Outstanding Balance | Payment processing flow starts immediately. User is redirected to payment confirmation or gateway. | Payment status is updated in the system after processing. | UNSUCCESFUL | FAILED
|  | RCS016 | AGENT | Agent can successfully log in with valid credentials. | 1. Open Agent Mobile App. 2. Enter valid username and password. 3. Click “Login.” | Agent account exists. | Username: Password | Redirected to agent dashboard. Login recorded in audit log. | Agent session active. | SUCCESSFUL | PASSED
|  | RCS017 | AGENT | login fails with invalid password. | 1. Open Agent Mobile App. 2. Enter valid username and wrong password. 3. Click “Login.” | Agent account exists. | Username: Password | Error message: “Invalid credentials.” No session created. | No changes to system. | SUCCESSFUL | PASSED
|  | RCS018 | AGENT | Agent can collect cash payment. | 1. Login to Agent Mobile App. 2. Tap “New Payment.” 3. Enter vehicle plate, driver phone, and payment amount. 4. Submit payment. | Agent logged in. | Vehicle: Phone: Amount | Payment recorded. Digital receipt generated. SMS confirmation sent. | Payment entry stored in database. | SUCCESSFUL | PASSED
|  | RCS019 | AGENT | Duplicate payment for same vehicle and time slot is rejected. | 1. Make payment for vehicle in current slot. 2. Attempt second payment for same vehicle within same slot. | Payment already recorded for vehicle in current period. | Vehicle: Amount | “Payment already recorded for this vehicle in this period.” | No duplicate record created. | SUCCESSFUL | PASSED
|  | RCS020 | AGENT | Agent can view payment history. | 1. Login to Agent Mobile App. 2. Go to “Payment History.” | Agent has at least one past transaction. | N/A | List of transactions with date, vehicle, and amount displayed. | No data changes. | SUCCESSFUL | PASSED
|  | RCS021 | AGENT | Agent can search payment history by vehicle plate. | 1. Login to Agent Mobile App. 2. Go to “Payment History.” 3. Search for specific vehicle. | Payments exist for that vehicle. | Vehicle | Only matching payments displayed. | No data changes. | SUCCESSFUL | PASSED
|  | RCS022 | AGENT | Invalid vehicle plate format is rejected. | 1. Tap “New Payment.” 2. Enter invalid plate (e.g., 12345). 3. Submit. | Agent logged in. | Vehicle Amount | “Invalid vehicle plate format.” | No payment recorded. | SUCCESSFUL | PASSED
|  | RCS023 | AGENT | Agent can edit a pending payment before submission. | 1. Tap “New Payment.” 2. Enter details. 3. Before submission, change payment amount. 4. Submit. | Payment not yet submitted. | Amount change | Updated amount saved. | Correct amount in database. | SUCCESSFUL | PASSED
|  | RCS024 | AGENT | Agent can cancel a pending payment before submission. | 1. Start new payment. 2. Tap “Cancel.” | Payment not submitted. | N/A | Payment entry discarded. | No database changes. | SUCCESSFUL | PASSED
|  | RCS025 | AGENT | offline payment capture is stored and synced when online. | 1. Disable internet on agent device. 2. Record a payment. 3. Reconnect to internet. 4. Sync data. | Offline capture feature enabled. | Vehicle Amount | Payment saved locally when offline. Synced successfully when online. | Payment appears in central database. | SUCCESSFUL | PASSED
|  | RCS026 | AGENT | Agent receives confirmation after payment submission. | Submit payment. | Agent logged in. | Vehicle Amount | “Payment successful” message displayed. Receipt number shown. | Confirmation stored in agent logs. | SUCCESSFUL | PASSED
|  | RCS027 | AGENT | Agent cannot record payment with zero amount. | 1. Tap “New Payment.” 2. Enter amount = 0. 3. Submit. | Agent logged in. | Vehicle Amount | Error: “Amount must be greater than zero.” | No payment recorded. | SUCCESSFUL | PASSED
|  | RCS028 | AGENT | Agent can log out successfully. | Tap “Logout.” | Agent logged in. | N/A | Redirected to login page. Session ended. | No active session. | SUCCESSFUL | PASSED
|  | RCS029 | AGENT | Session times out after inactivity. | 1. Login as agent. 2. Remain idle for timeout period. 3. Try to navigate to another page. | Timeout | N/A | Redirected to login page. | Session closed. | UNSUCCESFUL | FAILED
|  | RCS030 | AGENT | parking slot count updates correctly | 1. Log in as Agent. 2. Check current parking slot availability. 3. Record a car parking in the system. 4. Check updated slot availability. 5. Record the same car checking out. 6. Check updated slot availability again. | Agent’s zone has defined parking capacity. | Initial Available Slots | After parking: Available Slots = Initial - 1 After checkout: Available Slots = Initial | Parking slot count reflects real-time changes. | UNSUCCESFUL | FAILED
|  | RCS031 | ADMIN | Admin can log in with valid credentials. | 1. Navigate to Admin Portal login page. 2. Enter Admin Username and Password. 3. Click Login. | Admin account exists and is active. | Username: Password: | Admin is redirected to the Admin Dashboard; login recorded in audit log with timestamp and IP. | Admin session is active. | SUCCESSFUL | PASSED
|  | RCS032 | ADMIN | login fails with invalid credentials. | 1. Open Admin Portal login page. 2. Enter valid username and wrong password. 3. Click Login. | Admin account exists. | Username: Password: | Login denied; error message “Invalid credentials”; no session created; failed attempt recorded in audit log. | No active session. | SUCCESSFUL | PASSED
|  | RCS033 | ADMIN | Admin dashboard displays summary KPIs and AI insights. | 1. Login as Admin. 2. Navigate to the Dashboard. 3. Observe widgets: Total Revenue (today), Transactions (count), Top Agents, Revenue Trend chart, AI Insights panel. | System has transaction data for at least the last 30 days. | N/A | All widgets load without error; numeric values match sums in the transactions DB; AI Insights displays latest model output and timestamp. | Dashboard view logged in audit. | SUCCESSFUL | PASSED
|  | RCS034 | ADMIN | Navigation to ‘Add System Role’ page | 1. Login as an admin user. 2. From the Admin dashboard, click on “Add System Role.” | Admin user is logged in and has role management permissions. | Valid admin credentials. | System navigates to the “Add System Role” page, displaying the role creation form. | User remains on the role creation page. | SUCCESSFUL | PASSED
|  | RCS035 | ADMIN | Mandatory fields validation in ‘Add System Role’ | 1. Navigate to the “Add System Role” page. 2. Leave mandatory fields blank (e.g., Role Name). 3. Click “Save/Submit.” | User is on the “Add System Role” page. | Blank role name, other fields empty. | System displays an error message (e.g., “Role Name is required”) and prevents submission. | No role is created in the system. | SUCCESSFUL | PASSED
|  | RCS036 | ADMIN | Creation of a new role with valid data | 1. Navigate to “Add System Role” page. 2. Enter a valid role name (e.g., “Cashier Supervisor”). 3. Select relevant permissions from the list. 4. Click “Save/Submit.” | User is on “Add System Role” page. | Name Description | System displays success message (e.g., “Role created successfully”) and adds role to the roles list. | New role is visible in the “System Roles” list. | SUCCESSFUL | PASSED
|  | RCS037 | ADMIN | Prevention of duplicate role names | 1. Navigate to “Add System Role” page. 2. Enter a role name that already exists (e.g., “Cashier”). 3. Select permissions and click “Save/Submit.” | Role with same name exists. | Role names | System displays error message (e.g., “Role name already exists”) and prevents saving. | No duplicate role is created. | UNSUCCESSFUL | FAILED
|  | RCS038 | ADMIN | Deletion of a role | 1. Navigate to “System Roles” list. 2. Click “Delete” on an existing role. 3. Confirm deletion in popup dialog. | Role exists in system. | Role Name | System prompts confirmation before deletion and removes role upon confirmation. | Deleted role no longer appears in the system. | UNSUCCESSFUL | FAILED
|  | RCS039 | ADMIN | edit functionality of existing role | 1. Navigate to “System Roles” list. 2. Click “Edit” on an existing role. 3. Change role name or update permissions. 4. Save changes. | At least one role exists in the system. | Existing role | Role details update successfully, and changes reflect in the roles list. | Updated role details are saved. | SUCCESSFUL | PASSED
|  | RCS040 | ADMIN | Session times out after inactivity. | 1. Login as admin. 2. Remain idle for timeout period. 3. Try to navigate to another page. | Timeout | N/A | Redirected to login page. | Session closed. | UNSUCCESFUL | FAILED
|  | RCS041 | CASHIER | Cashier dashboard loads successfully | 1. Login as a cashier. 2. Navigate to the dashboard from the main menu. | Cashier account exists and is active. | cashieruser, password | Dashboard loads showing summary details (pending handovers, verified handovers, assigned agents). | Cashier is on the dashboard page. | SUCCESSFUL | PASSED
|  | RCS042 | CASHIER | Dashboard displays correct pending handovers count | 1. Login as a cashier. 2. Navigate to dashboard. 3. Compare displayed pending handovers count with records in Pending Handovers page. | System has at least one pending handover. | Transaction records | Count matches the number of pending handovers in records. | None. | SUCCESSFUL | PASSED
|  | RCS043 | CASHIER | Dashboard data refresh functionality | 1. Login as cashier. 2. On dashboard, trigger refresh button | Dashboard has data that can change. | Trigger an agent payment to create pending handovers. | Dashboard updates with new counts and totals. | Data remains consistent. | SUCCESSFUL | PASSED
|  | RCS044 | CASHIER | View pending handovers list | 1. Login as cashier. 2. Click on “Pending Handovers” menu. | At least one pending handover exists. | Transaction | List displays with Handover ID, Agent Name, Amount, and Date. | None. | SUCCESSFUL | PASSED
|  | RCS045 | CASHIER | search functionality in pending handovers | 1. Navigate to pending handovers page. 2. Enter known Handover ID in search field. | Handover ID exists. | Handover ID | Matching record(s) displayed. | None. | SUCCESSFUL | PASSED
|  | RCS046 | CASHIER | Action to mark handover as verified | 1. On Pending Handovers, select a handover. 2. Click "Verify". | Handover exists in pending state. | Handover ID | Handover moves to Verified Handovers list. | Status updated in system. | SUCCESSFUL | PASSED
|  | RCS047 | CASHIER | View verified handovers list | 1. Login as cashier. 2. Click “Verified Handovers” menu. | At least one handover has been verified. | Verified handover | List displays Handover ID, Agent, Amount, Date Verified | None. | SUCCESSFUL | PASSED
|  | RCS048 | CASHIER | View assigned agents in profile | 1. Login as cashier. 2. Navigate to profile. | Cashier has assigned agents. | CashierID | List of assigned agents displayed with agent name, ID, and zone. | None. | SUCCESSFUL | PASSED
|  | RCS049 | CASHIER | assigned agents display correct data | 1. Open profile page. 2. Compare list with DB data. | DB has assigned agents. | DB agent assignment table. | Data matches exactly. | None. | SUCCESSFUL | PASSED
|  | RCS050 | CASHIER | View zones and associated agents | 1. Login as cashier. 2. Navigate to “Zones & Agents” page. | Zones and agents exist in system. | Zone | Page displays zones with agents mapped to them. | None. | SUCCESSFUL | PASSED
|  | RCS051 | CASHIER | accuracy of agents under a zone | 1. Navigate to Zones & Agents. 2. Compare list with DB mapping. | Zone-agent assignments exist. | DB mapping table | Data matches DB. | None. | SUCCESSFUL | PASSED

## TEST EXECUTION RESULT CHART
Project Name | Revenue Collection System | Developer Name |  | JAMES MUNIU | Pre-requisite
Product Name | REVENUE COLLECTION | Developer Test Evidence |  | YES | hosted Application
Version | 1.0.0.100420251315 | Test Designed by |  | MERCELYN KADIMA | Running scripts
Release Number | 1 | QA Engineer Name |  | MERCELYN KADIMA
Target Client | IN-HOUSE | QA Report date |  | 2025-08-12
Applicable Branch |  | Environment |  | Test Server
Country
TEST EXECUTION
Section | Test Cycle | Status | Total Test Case | Test cases Executed | Not Executed | Passed | Failed | Blocked | Test Coverage | Pass Rate
CUSTOMER PORTAL | Cycle 1 | Completed | 15 | 15 | 0 | 12 | 3 | 0 | 100% | 80%
AGENT | Cycle 1 | Completed | 15 | 15 | 0 | 13 | 2 | 0 | 100% | 86.67%
ADMIN | Cycle 1 | Completed | 10 | 10 | 0 | 7 | 3 |  | 100% | 70%
CASHIER | Cycle 1 | Completed | 11 | 11 | 0 | 11 | 0 | 0 | 100% | 100%
Pass Rate | [8 empty] | 100% | 84.17%
TOTAL |  |  | 51 | 51 | 0 | 43 | 8 | 0
KEY:
[12 empty] | >80 | Above threshold
[12 empty] | >70 | Below threshold but on track
[12 empty] | <70 | Below threshold and running late
[12 empty] | N/A | Blocked

## BugTracker
Project Name | Revenue Collection System | Developer Name | JAMES MUNIU | Pre-requisite |  | Total testcases | 553
Product Name | Revenue Collection System | Developer Test Evidence | YES |  |  | Test cases tested | 553
Version | 1.0.0.100420251315 | Test Designed by | MERCELYN KADIMA |  |  | To be Tested | 0
Release Number | 1 | QA Engineer Name | MERCELYN KADIMA |  |  | Blocked | 0
Target Client | IN HOUSE | QA Report date | 2025-08-12 |  |  | Passed | 545
Applicable Branch |  | Environment | Test Server |  |  | Failed | 8
Country
Test case/ Defect ID | Defect Description | Steps to Reproduce | Expected Results | Actual Results | Created On | Created By | Severity | Priority | Status | Assigned Date | Assigned To | Resolution | Resolution Date | Estimated Time To Fix | Actual Time To Fix | Root Cause
RCS001 | Customer registration via self-service portal. | 1. Navigate to self-service portal. 2. Click “Register.” 3. Enter Name, email, Phone, Password. 4. Submit the registration form. | Account is created successfully. Success message displayed. SMS confirmation sent to registered phone number. | No SMS confirmation sent to registered phone number. |  | Mercelyn Kadima
RCS012 | Customer is logged out after session timeout. | 1. Login to portal. 2. Stay idle for timeout duration. 3. Attempt to navigate to another page. | Redirected to login page. Message: “Session expired.” | No session timeout |  | Mercelyn Kadima
RCS015 | Initiate Payment button functionality | 1. Navigate to Payment section. 2. Click Initiate Payment button. | Payment processing flow starts immediately. User is redirected to payment confirmation or gateway. | No payment processing is initiated |  | Mercelyn Kadima
RCS029 | Session times out after inactivity. | 1. Login as agent. 2. Remain idle for timeout period. 3. Try to navigate to another page. | Redirected to login page. | No session timeout |  | Mercelyn Kadima
RCS030 | Parking slot count updates correctly | 1. Log in as Agent. 2. Check current parking slot availability. 3. Record a car parking in the system. 4. Check updated slot availability. 5. Record the same car checking out. 6. Check updated slot availability again. | After parking: Available Slots = Initial - 1 After checkout: Available Slots = Initial | Parking slot remains the same |  | Mercelyn Kadima
RCS037 | Prevention of duplicate role names | 1. Navigate to “Add System Role” page. 2. Enter a role name that already exists (e.g., “Cashier”). 3. Select permissions and click “Save/Submit.” | System displays error message (e.g., “Role name already exists”) and prevents saving. | System saves duplicate role names
RCS038 | Deletion of a role | 1. Navigate to “System Roles” list. 2. Click “Delete” on an existing role. 3. Confirm deletion in popup dialog. | System prompts confirmation before deletion and removes role upon confirmation. | System doesn't delete the role
RCS040 | Session times out after inactivity. | 1. Login as admin. 2. Remain idle for timeout period. 3. Try to navigate to another page. | Redirected to login page. | No session timeout
Note on I10: Raj: Choose from the dropdown list
Note on J10: Raj: Choose from the dropdown list